## Ark1
Task | Start date | Days used | Kolonne1
Project manager | 2019-05-27 | 16 |  | Project managment,costumer contact and contract
Project manager,Content,Develper | 2019-05-27 | 1 |  | Initial meeting
Project manager,Content Develper,Designer | 2019-05-27 | 2 |  | Research
Content Developer,Designe | 2019-05-28 | 2 |  | Planning the website
Project manager,Content,Developer,Designer | 2019-05-29 | 3 |  | Planing the content on the page
Content Developer | 2019-05-30 | 2 |  | Building styletiles and other.
Content Develpoer,Designer,Developer | 2019-05-31 | 4 |  | Developing the content and text.
Designer | 2019-06-01 | 5 |  | Take pictures of the products.
Content developer,Copywriter | 2019-06-01 | 3 |  | Testing and planing the site
Photograph | 2019-06-01 | 5 |  | HTML/CSS
Content developer,Designer | 2019-06-05 | 2 |  | Going over the site looking for mistakes or other.
Developer | 2019-06-04 | 7 |  | Last meeting and lauching the page
Content developer, Designer,Developer | 2019-06-12 | 1
Project maager, Content developer,Designer,Developer | 2019-06-13 | 1